Interdisciplinarity / LA & SS Task Force

Minutes
April 23, 2026 
9:15–10:30 a.m.

Via TEAMS

Attendance

Present K. Bantley, C. Brewer, E. Chen, D. Decarlo, H. de Savage, J. Gamache, T. Garceau, G. Gigliotti, K. Larsen, H. Rodriguez, J. Tully

- Approval of Minutes of April 9, 2026 (H. de Savage – Mot. To App., C. Brewer– 2nd) – Approved

- Approval of Minutes of April 16, 20206 (T. Garceau – Mot. To App., H. de Savage – 2nd)

-Approved

- Updates:

- Faculty focus groups – unilateral support for LA/SS in all 3 groups

- Meeting with Consultant – We should start thinking about how we will write our report. This will not happen until the data is all gathered and analyzed.

- Steering Committee

- Draft outline of larger report was circulated, will share with group when finalized.

- The deadline to submit our report is firm. This is due to providing those involved with the next stage of the larger university report having ample time to complete their work.

- Draft language for Alumni/Student forums and decorum

  - Language for all three groups are in Teams folder.

  - H. Rodriguez to lead undergrad forums

  - J. Tully to lead grad. forums

- Questions for Student/Alumni forums

- Language for three groups in Teams folder.

- All agreed that if we have at least three in each session, focus groups will run. If morning session low, will ask students to move to the afternoon.

- Survey – follow up from focus groups

- Team teaching survey is out

- IDP survey is out…reminder was also sent out

- Student survey to go out Friday

- Faculty, staff, alumni survey to go out Monday – J. Gamache to create with Microsoft Forms

- Faculty/Staff survey ask Provost office to send

- Alumni survey – ask L. Bigelow to send

- Analysis – May work

- All focus groups/surveys completed by May 1st

- Focus groups

    - Tim G. to type notes from recording for alumni

    - John T. to type notes from recording for graduate students

    - K. Bantley to type notes from recordings for undergraduate students

    - C. Brewer, H. de Savage, & H. Rodriguez to aggregate common themes from all focus groups

- Surveys

- G. Gigliotti & K. Larsen to analyze IDP and Team-teaching surveys

- H. Rodriguez to analyze student survey from Qualtrics

- J. Tully to analyze information from employers via C. Sterling office

- Theme of our report – Summaries with quotes

Meeting adjourned at 10:32

Respectfully submitted,

K. Bantley